## tasks
| item | Assign to | status | Remark | start Date | due date | complition date
1 | money from yasin | rakib | pending | 500 paid
2 | pilot hand over (booking site) | rakib | handded over
3 | pilot pic update | sajib | done |  |  |  | april 2nd week
4 | plum websie color correction | rownak | continue | rawnak shall explain
5 | dashboard BR | rawnak and sajib | ongoing |  |  | 30-04
6 | getting a power bi licence (premium) | rownak and saimu bhai | complete | delayed 2 days
7 | building the nizams package app | sajib and rawnak
| presentation proposal for phase |  | done
| undetstading the entire existing system in debpt |  | done |  |  |  | finised in may 2nd week
| ensure the first phase |  | done
| demo |  | done | 25th internal time line
8 | chatting app | Rownak and sajib | on pause
9 | e-commerce | rakib | on going | rakib is being helped by anny | 16-4 | 30-4
10 | suncrop website | imran, rownak shall supervise |  | need to create the content |  | 30-04
11 | cargo dashboard design | raownak and shafiq bhai | on going |  |  | TBD
12 | suncrop parts puchase | sajib | on going | needs to make decession
13 | spreay delivery to suncrop | shihab and rakib | on going |  |  |  | 29-5
14 | deliver the server from zam bd to suncrop kamlapure | rakib | to be deliverd |  |  | 30-5 | 29-5
| followup with Yasin | rakib | to be delivered | payment 500 the product shown buy the new domain and host it
| parbottipure station shows kulna's train |  |  | train number requested waiting for replay from arif bhai
| fix zam4u.com |  | done
| centrlize all the domians & hosting |  |  | only zam4 u pending¦ date will be fixed after mahim bhai passes it
| put zam all pasword to a excell file with details | sajib | pending |  |  | 31-5
15 | meeting on 18th with sigma | whole team | done |  |  | 18-5
16 | Data flow diagram needs to be delivered to sigma |  | ongoing | Done but not good | 19-5 | 24-5
17 | get the flow chart from sigma |  | done | Done but not good | 19-5 | 19-5
18 | engage hakimi with rawnak | rawnak and haqimi(sigma) | ongoing | priority high | TBD
19 | formula for oil container for tuhin sir | sajib | ongoing |  |  | 25-5 | expecting 30-5
20 | presentation for power bi single user vs multi user licence | sajib |  |  |  | 3-6'
21 | pilot website hjostig selection |  |  | priority high we should settel it asap
22 | every week Thursday progress report |  |  | priority high
23 | product demo with nizam |  |  | done with 50% success |  | 7th june
24 | recheck the transformation | sajib |  |  |  | 2022-09-06
25 | host the middle ware and frontend | sajib |  |  |  | 2022-07-06
26 | get rest of the front end materials from sigma | rownak |  | to be complited by sigma
27 | Add Identity and refine middle ware | sajib
29 | itinerary document needs to be done |  |  |  |  | 2022-08-06 | 2022-08-06
30 | demo with nizam |  |  |  |  | 2022-06-14
31 | take a look at all the feedbacks | sajib and rownak |  |  |  | 20/6/2022
32 | take all the data from suncrop and split them | sajib
33 | rework pilot booking site | rownak
34 | optimize transformation performance | sajib
35 | meeting summary | sigma
36 | deliver the link to sigma | sajib
35 | update pilot site | rownak
36 | train dashboard front architechture | rownak
37 | train dashboard backend | sajib
38 | power flow | rownak
39 | api data upload | sajib | done |  |  | 2022-01-09 | 2022-01-09
40 | All expriry date to saimu bhai | sajib | ongoing | still collecting |  | 2022-01-09
41 | chat server | sajib | done | java script and blazore front admins pending |  | 2022-04-09 | 2022-04-09
42 | train dashboard front | rownak | done |  |  |  | 2022-05-09
43 | ecommerce | not assigned | not started yet | not enough resources |  | to be decleard
44 | chat front pure js |  |  | to be discussed and decide date
45 | chat front react
46 | chat front word press

## etl
no | item | zam | sigma | remark | status
1 | quality_rules_library_page.pbix
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31